## Лист1
What | Status | Date | Comment
PCBs for 35 PMs and 7 TCMs | ready by | 2020-01-20
Components for one PM and one TCM packed and transferred to the factory | ready by | 2020-01-24
Assembly of 1 PM and one TCM | start | 2020-01-27
| ready by | 2020-02-17
Firmware for TCM final test | ready by | 2020-02-01
Final test with 12 channel detector prototype, two PMs and TCM at INR starts | start | 2020-02-17
| ready by | 2020-03-10
Shipping out 2 PMs and 1 TCM to CERN from INR | ready by | 2020-03-11
Shipping out all FTA mechanics & optical components and 1 splitter box to CERN from INR | ready by | 2020-03-11
2 PMs, 1 TCM, FTA mechanics & optics delivered to CERN | ready by | 2020-03-17
Testing of full chain (1 PMT -> 2 PMs -> TCM -> CRU, LTU, FLP) | start | 2020-03-17
| ready by | 2020-03-27
Preparations for PRR | start | 2020-03-17
| ready by | 2020-03-30
Final PRR | ready by | 2020-04-01
First version of the FIT readout integration (FT0+FV0+FDD) | ready by | 2020-04-01
V0 and FDD front-end specs | ready by | 2020-04-01
Production of 34 PMs and 6 TCMs | start | 2020-04-02
| ready by | 2020-04-25 | not realistic
Testing of all PMs and TCMs | start | 2020-04-26
18 PMs for FT0 tested | ready by | 2020-09-04
Testing of the remaining 8 PMs and 2 TCMs | start | 2020-09-05
Testing of the remaining 8 PMs and 2 TCMs | ready by | 30.10.2020 | in case of 1 PM/week
Assembly of one air-cooled Wiener crate in the FIT lab at CERN | start | 2020-02-10
| ready by | 2020-02-20
Assembly of the water-cooled crates at CERN and mounting them in racks | start | 2020-03-20
| ready by | 2020-04-10
First DCS/WinCC version for the readout integration tests | ready by | 2020-05-12 | to be checked before 23.01.2020
Ready for the standalone integration test
FTC instllation at P2 | ready by | 2020-06-02
FIT-A installation at P2 | start | 2020-10-06
FIT-A installation at P2 | ready by | 2020-10-12
Installation of 10 all FTC PMs and TCMs at P2 | start | 2020-04-02
| ready by | 2020-06-28
Installation of all FIT-A PMs and TCMs at P2 | start
| ready by | 2020-11-16